Body Camera Report

Introduction

Initial Research Began Spring 2014

Ferguson Happened---increased the need to look at BWCs

Developed initial estimates for needs (# of cameras, data, staffing)

Applied for fed grants spring 2015

No money….decided to move forward with a pilot program to shape RFP process and assess cost

Policy Development

Federal Reports

Sample Policies

Model Policy

FOP Policy

Legislative issues

Pilot Program

Design

90 day, 3 groups 1 month each, 12 body/12 flex,

Group 1 (totals and averages)

Group 2 (totals and averages)

Group 3 (totals and averages)

Training

Policy

Tech

Evidence.com

Pilot Review

Survey Results (Baseline vs.3 waves)

Survey-Public input

Media involvement – Mike Bush

IT-needs assessment

Summary

Limits of the Eval/Pilot

Recommendations

Test Back end

Look at other camera options

Car Cam integration

Adequate staffing

Legislative changes